## Gantt Chart
| MIS 322: | [6 empty] | Gantt Chart Template © 2020 by Vertex42.com
| TEAM B |  |  |  |  | Project Start: | 2021-09-29
| Project Manager |  |  |  |  | Display Week: | 1 | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15
 | time axis 2021-09-27 to 2021-11-21
Task ID | TASK | Team Assignment | PROGRESS |  | START | DAYS | END | time axis 2021-09-27 to 2021-11-21
| Phase 1 |  |  | - | 2021-09-29 |  | 2021-11-01
1.1 | Create Team Charter | PM | 100% |  | 2021-09-29 | 12 | 2021-10-10
1.2 | Interview questions to Customers | Everyone | 100% |  | 2021-10-04 | 14 | 2021-10-17
1.3 | Post Interview Review | Everyone | 100% |  | 2021-10-11 | 14 | 2021-10-24
1.4 | Interview Questions to Customer (instructor) | Everyone | 100% |  | 2021-10-24 | 8 | 2021-10-31
1.5 Project Manager
1.51 | Create Project Plan Lite | PM | 100% |  | 2021-10-17 | 7 | 2021-10-24 | bar: 2021-10-11 to 2021-10-24
1.52 | Create Initial Visioning Document | PM | 100% |  | 2021-10-11 | 14 | 2021-10-24 | bar: 2021-10-11 to 2021-10-24
1.6 Database Administrator
1.61 | Identify Data Elements | DBA | 100 |  | 2021-10-19 | 1 | 2021-10-19
1.62 | Identify Tables and Assign | DBA | 100 |  | 2021-10-20 | 1 | 2021-10-20
1.63 | Identify Primary and Foreign KEYS | DBA | 100 |  | 2021-10-21 | 1 | 2021-10-21
1.64 | Enforce Relationship Between Tables | DBA | 100 |  | 2021-10-22 | 1 | 2021-10-22
1.65 | Normalize the System | DBA | 100 |  | 2021-10-25 | 1 | 2021-10-25
1.66 | Identify Columns to be INDEXED | DBA | 100 |  | 2021-10-25 | 1 | 2021-10-25
1.7 Process & UI
1.71 | Start User Documentation - Build Layout | Process & UI | 10% |  | 2021-10-25 | 7 | 2021-11-01
1.8 Process Modeler
1.81 | List of Current Steps in Business Process | Process | 100% |  | 2021-10-25 | 6 | 2021-10-31
1.82 | Identify Possible Changes in Business Process | Process | 10% |  | 2021-10-25 | 6 | 2021-10-31
1.9 UI/UX Designer
1.91 | Identify Users | UI | 100 |  | 2021-10-25 | 6 | 2021-10-31
1.92 | Identify UIs Needed | UI | 100 |  | 2021-10-25 | 6 | 2021-10-31
-
| Phase 2 |  |  | - | 2021-10-25 |  | 2021-11-11
2.1 | Interview Qs to Customers II | Everyone | 100% |  | 2021-10-25 | 6 | 2021-10-31
2.2 | Post Interview 2 | Everyone |  | - | 2021-10-28 | 13 | 2021-11-10
2.3 | Team Evaulation (Individual) | Everyone (individual) | 100 |  | 2021-10-25 | 13 | 2021-11-07
2.4 | Presentation 1 | Everyone | 100 |  | 2021-11-01 | 6 | 2021-11-07
2.5 Project Manager
2.51 | Risk Assessment | PM | 100 |  | 2021-10-25 | 6 | 2021-10-31
2.52 | Update Project Plan | PM | 80 |  | 2021-10-25 | 13 | 2021-11-07
2.53 | Start Presentation Slides | PM | 50% |  | 2021-10-25 | 1 | 2021-10-30
2.54 | Project Binder 1 | PM | 90 |  | 2021-10-25 | 13 | 2021-11-07
2.6 Database Administrator
2.61 | Create Constraints | DBA |  | - | 2021-10-26 | 3 | 2021-10-28
2.62 | Alter Database (if needed) | DBA |  | - | 2021-10-26 | 1 | 2021-10-26
2.63 | Create any SEQUENCES | DBA |  | - | 2021-10-27 | 3 | 2021-10-29
2.64 | Create any VIEWs | DBA |  | - | 2021-10-27 | 2 | 2021-10-28
2.65 | Code any SCRIPTS | DBA |  | - | 2021-10-29 | 4 | 2021-10-26
2.66 | Code any stored procedures, functions and triggers | DBA |  | - | 2021-10-29 | 4 | 2021-11-03
2.67 | Manage Transactions and lockings | DBA |  | - | 2021-11-04 | 4 | 2021-11-09
2.68 | Manage Database Security | DBA |  | - | 2021-11-10 | 2 | 2021-11-11
2.69 | Work with XML and BLOB's | DBA |  | - | 2021-11-10 | 1 | 2021-11-10
2.7 Process & UI
2.71 | Work on User Documentation | Process & UI |  | - | 2021-11-01 |  | TBD
2.8 Process Modeler
2.81 | AS-IS Activity Diagrams | Process |  | - | 2021-10-31 | 7 | 2021-11-07
2.9 UI/UX Designer
2.91 | Begin Organize how User will Navigate the System | UI |  | - | 2021-11-01 | 6 | 2021-11-07
2.92 | Generate UI interface mockups | UI |  | - | 2021-11-01 | 6 | 2021-11-07
2.93 | Start User Documentation | UI |  | - | 2021-11-08 |  | TBD
| Phase 3 |  |  | - | 2021-11-08 |  | 2021-12-12
3.1 | Assignment 3 | Everyone (individual) |  | - | 2021-11-08 | 6 | 2021-11-14
3.2 | Presentation Participation | Everyone (individual) |  | - | 2021-11-08 | 6 | 2021-11-14
3.3 | Final Interview to Customer | Everyone |  | - | 2021-11-15 | 6 | 2021-11-21
3.4 | Assignment 4 | Everyone (individual) |  | - | 2021-11-22 | 6 | 2021-11-28
3.5 | Assignment 5 | Everyone (individual) |  | - | 2021-11-29 | 6 | 2021-12-05
3.6 | Team Peer Evaluation 2 | Everyone (individual) |  | - | 2021-11-29 | 6 | 2021-12-05
3.7 | Project Documentation | Everyone |  | - | 2021-11-29 | 13 | 2021-12-12
3.8 | Final: Presenation 2 | Everyone |  | - | 2021-11-22 | 20 | 2021-12-12
3.9 Project Manager
3.91 | Create/work on necessary documents + Share | PM |  | - | 2021-11-08 | 13 | 2021-11-21
3.92 | Test Plan Update | PM |  | - | 2021-11-08 | 34 | 2021-12-12
3.93 | Work on Presentation 2 | PM |  | - | 2021-11-22 | 20 | 2021-12-12
4.0 Database Administrator
4.01 | CLR Integration | DBA |  | - | 2021-11-08 | 34 | 2021-12-12
4.1 Process Modeler
4.11 | Update Diagrams | Process |  | - | 2021-11-08 | 34 | 2021-12-12
4.2 UI/UX Designer
4.21 | Use Case Design Discovery (Is this only for UI or both UI + Process?) | UI |  | - | 2021-11-08 | 6 | 2021-11-14
4.22 | UI Design, Report Design | UI |  | - | 2021-11-08 | 34 | 2021-12-12
4.23 | User Documentation | UI |  | - | 2021-11-08 | 34 | 2021-12-12
|  |  |  | - |  | 0
|  |  |  | - |  | 0
|  |  |  | - |  | 0
|  |  |  | - |  | 0
|  |  |  | - |  | 0

## Help
Help
Instead of detailed help worksheet, please do the following if you have questions about how this spreadsheet works, or how to use this spreadsheet.
1) Watch the Video Tutorial on YouTube
https://youtu.be/8eKk0M2zGIk
2) Read the Following Page
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Although the content on the above page was created originally for the Excel template, most of the information about the use of formulas and ways to customize the Gantt chart apply just as well to the Google Sheets version.
Formula for % Complete of a summary task, based on its sub tasks:
SUMPRODUCT(days_range,percent_complete_range)/SUM(days_range)
To show the % Complete within the bars in the Gantt chart:
Select a cell within the Gantt chart area and go to Format > Conditional Formatting, then "turn on" the grey bar rule by changing 1=0 to 1=1 within the AND function.

## TermsOfUse
Simple Gantt Chart for Google Sheets
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2020 Vertex42 LLC. All rights reserved.
This template is a copyrighted work under the Unites States and other copyright laws and is the property of Vertex42 LLC. The items listed below are additional points to help clarify how you may use this template.
You may make archival copies and customize this template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within this template.
This template and any customized or modified version of this template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on a public server.
The Share Settings for this spreadsheet must always be set to "Private"
Limited Private Sharing and Other Allowed Uses
See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html

## GanttChartPro
Gantt Chart Template Pro for Google Sheets
Gantt Chart Template Pro, by Vertex42.com, is a spreadsheet template designed originally for Microsoft Excel that offers more features than the free version. When you purchase it, you will also get a link to download the Pro version for Google Sheets!!
Learn More About Gantt Chart Template Pro
- Visit the web page above to view screenshots and watch demo videos
Features in the Pro version for Google Sheets
Define task durations by specifying the number of Work Days
- In this free version, the inputs to define a task are the Start Date and the Calendar Day duration. In the Pro version, the default option is to enter the Start Date and the number of Work Days.
Choose whether to define task durations using Calendar Days or Work Days or End Dates
- The Pro version includes a larger set of template rows that provide more options for defining the Start date, End date, duration, and dependency of tasks.
Exclude holidays from work days
- List holidays and other non-working days in a separate sheet. When defining task durations using Work Days, these dates will be excluded.
Define what you mean by "Weekend" when using Work Days
- The Pro version allows you to define exactly which day(s) of the week you want to use as your weekend. The default is Saturday and Sunday.
Color-Code bars in the Gantt chart
- The Pro version includes a column for entering a color code like "k", "r", or "y" to change the color of the bars in the Gantt chart. The Help worksheet explains some advanced formulas that you could use in the Color column to automatically color a bar based on the name in the Lead column.
Define tasks dependences by specifying the predecessor WBS
- The template rows include an option for entering a Predecessor WBS. The Start date will be calculated as the day following the End date of the predecessor.